## Effort Estimation for DWH
Effort Estimation to setup Datawarehouse_corp in synapse
Report Name | Tables Need in DataWarehouse | Effort needed to create pipeline
| Schema Creation Synapse Datawarehouse with constraint validation | 88 hrs
| Analyzing the existing ETL logic(atleast 6hr per table) | 390 hrs
Report 1 | Retail_tblMBranch_Common | 6 hrs
| Retail_tblMaster | 6 hrs
| Retail.dbo.tblTransDet (ACLSG) | 10 hrs
Retail.dbo.tblTransDet(MCSG)
| Retail.dbo.tblTransHdr (ACLSG) | 6 hrs
Retail.dbo.tblTransHdr(MCSG)
| Retail.dbo.tblStk (ACLSG) | 10 hrs
Retail.dbo.tblStk(MCSG)
| Retail.dbo.tblMBranch (ACLSG) | 6 hrs
Retail.dbo.tblMBranch(MCSG)
| Retail.dbo.tblMaster(ACLSG) | 6 hrs
Retail.dbo.tblMaster(MCSG)
Report 2 | Code_cd_company_Common | 10 hrs
| Code_cd_prodrefgroup_mapping_Common | 8 hrs
| Code_cd_prodrefgroup_Common | 8 hrs
| Code_cd_prodcat_Common | 6 hrs
| Code_cd_productgroup_Common | 10 hrs
| Code_cd_producttype_Common | 10 hrs
| Code_cd_gemtype_Common | 8 hrs
| Code_cd_goldtype_Common | 8 hrs
| Code_cd_goldcontent_Common | 10 hrs
| Inventory_inv_tblcollectorbrand_Common | 10 hrs
| MCPDMSCentral_tblBranch | 6 hrs
| MCPDMSCentral_tblCompany | 6 hrs
| MCPDMSCentral_tblMaster | 6 hrs
| MCPDMSCentral_tbl_MRetailMaxiBranch | 6 hrs
| MCPDMSCentral_tblGoldType | 10 hrs
| MCPDMSCentral_tblCustomer | 10 hrs
| MCPDMSCentral_tblTicketDetails | 10 hrs
| MCPDMSCentral_tblTicket | 10 hrs
| MCPDMSCentral_tblLOF_Historical | 10 hrs
| MCPDMSCentral_tblRedeem_Renew | 10 hrs
| MCPDMSCentral_tblPolice_Seized | 10 hrs
| MCPDMSCentral_tblLOF_HQDispose_MaxiCash_Singapore | 6 hrs
| MCPDMSCentral_tblSecUser | 10 hrs
| MCPDMSCentral_tbl_MRetailMaxiBranch | 6 hrs
| Retail_tblInstalmentHdr_MaxiCash_Singapore | 8 hrs
| Retail_tblInstalmentItem_MaxiCash_Singapore | 8 hrs
| Retail_tblInsCustOrder_MaxiCash_Singapore | 8 hrs
| Retail_tblDepOffset_Common | 8 hrs
| Retail_tblTransDet_Common | 10 hrs
| Retail_tblStk_Jewellery_Singapore | 6 hrs
| Retail_tblStk_Common | 10 hrs
| Retail_tblCustOrder_Common | 10 hrs
| Retail_tblStk_MaxiCash_Singapore | 6 hrs
| Retail_tblStkBag_MaxiCash_Singapore | 10 hrs
| Retail_tblstkWatch_MaxiCash_Singapore | 10 hrs
| Retail_tblPromorep_Common | 10 hrs
| Retail_tblTransHdr_Common | 10 hrs
| Retail_tblMPromoRep_Common | 10 hrs
| Retail_tblTransDet_MaxiCash_Singapore | 10 hrs
| Retail_tblCustServDet_Common | 10 hrs
| Retail_tblCustomer_Jewellery_Singapore | 6 hrs
| Retail_tblCustomer_MaxiCash_Singapore | 6 hrs
| Retail_tblCustomer_Common | 10 hrs
| Retail_tblCust_Membership_Common | 10 hrs
| Retail_tblSecUser_Common | 10 hrs
| Retail_tblIndvStoreAnalysTar_Common | 10 hrs
| Retail_tblIndvStoreAnalysTar_Jewellery_Singapore | 10 hrs
Report3 | Inventory_Inv_tblBulk_Common | 10 hrs
| Inventory_Inv_tblMaster_Common master_Blk_TradeInPurpose | 6 hrs
| Inventory_Inv_tblPurpose_Common | 10 hrs
| Retail_tblMonthEndBalance_Common | 6 hrs
| Retail_tblSecGroups_Common | 10 hrs
| Validating and scheduling the trigger for pipeline | 80 hrs
| Total | 1060 hrs

## Effort Estimation for Datamart
Effort Estimation to setup Datawarehouse_corp in synapse
Report Name | Tables Need in Datamart | Effort needed to create pipeline
| Creating Schema and validating constraints | 20 hrs
Report 1 | Master_Branch | 12 hrs
| v_Today_Retail_Transaction | 15 hrs
| Validating and Scheduling the trigger for pipeline | 20 hrs
Report 2 | Analysing the Existing ETL logic | 120 hrs
| Lookup_Items_CategoryLevel1 | 15 hrs
| Lookup_Customer_Information | 15 hrs
| Lookup_Pawner_Information | 20 hrs
| Lookup_Pawner_Personal_Info | 18 hrs
| Lookup_Product_Line | 15 hrs
| Lookup_Staff | 18 hrs
| Lookup_Store_Target | 18 hrs
| Txn_pawn | 20 hrs
| Txn_Sales | 20 hrs
| Lookup_PLMS_Others | 18 hrs
| Lookup_Items | 20 hrs
| Validating and Scheduling the trigger for pipeline | 40 hrs
| Analysing the Existing ETL logic | 54 hrs
Report 3 | Lookup_bulkin | 20 hrs
| Summary_Item_Holder_and_Movement | 20 hrs
| Validating and Scheduling the trigger for pipeline | 24 hrs
| Total | 542 hrs

## Effort estimation for changes in Tableau
Report Name | Activity needed | Time taken
Report 1 | Downloading and analysing existing model | 5 hrs
| Creating Data model using Synapse server | 4 hrs
| Solving column issues in dashboard | 3 hrs
| Extraction and validation | 4 hrs
Report 2 | Downloading and analysing existing model | 16 hrs
| Creating 2 data models using synapse server | 12 hrs
| Solving column issues in dashboards | 8 hrs
| Extraction and validation | 24 hrs
Report 3 | Downloading and analysing existing model | 10 hrs
| Creating 2 data models using synapse server | 8 hrs
| Solving column issues in dashboards | 4 hrs
| Extraction and validation | 10 hrs
| Publishing reports to server and scheduling | 8 hrs
| Total | 116 hrs