## Effort estimation for DWH
Effort Estimation to setup Datawarehouse_corp in synapse
Report Name | Tables Need in DataWarehouse | Effort needed to create pipeline
| Schema creation in datawarehouse | 17 hrs
Report 1 | Retail_tblMBranch_Common | 2 hrs
| Retail_tblMaster | 2 hrs
| Retail.dbo.tblTransDet (ACLSG) | 1 hrs
Retail.dbo.tblTransDet(MCSG)
| Retail.dbo.tblTransHdr (ACLSG) | 1 hrs
Retail.dbo.tblTransHdr(MCSG)
| Retail.dbo.tblStk (ACLSG) | 1 hrs
Retail.dbo.tblStk(MCSG)
| Retail.dbo.tblMBranch (ACLSG) | 1 hrs
Retail.dbo.tblMBranch(MCSG)
| Retail.dbo.tblMaster(ACLSG) | 1 hrs
Retail.dbo.tblMaster(MCSG)
Report 2 | Code_cd_company_Common | 2 hrs
| Code_cd_prodrefgroup_mapping_Common | 2 hrs
| Code_cd_prodrefgroup_Common | 2 hrs
| Code_cd_prodcat_Common | 2 hrs
| Code_cd_productgroup_Common | 2 hrs
| Code_cd_producttype_Common | 2 hrs
| Code_cd_gemtype_Common | 2 hrs
| Code_cd_goldtype_Common | 2 hrs
| Code_cd_goldcontent_Common | 2 hrs
| Inventory_inv_tblcollectorbrand_Common | 2 hrs
| MCPDMSCentral_tblBranch | 1 hrs
| MCPDMSCentral_tblCompany | 1 hrs
| MCPDMSCentral_tblMaster | 1 hrs
| MCPDMSCentral_tbl_MRetailMaxiBranch | 2 hrs
| MCPDMSCentral_tblGoldType | 1 hrs
| MCPDMSCentral_tblCustomer | 1 hrs
| MCPDMSCentral_tblTicketDetails | 1 hrs
| MCPDMSCentral_tblTicket | 1 hrs
| MCPDMSCentral_tblLOF_Historical | 1 hrs
| MCPDMSCentral_tblRedeem_Renew | 1 hrs
| MCPDMSCentral_tblPolice_Seized | 1 hrs
| MCPDMSCentral_tblLOF_HQDispose_MaxiCash_Singapore | 1 hrs
| MCPDMSCentral_tblSecUser | 1 hrs
| MCPDMSCentral_tbl_MRetailMaxiBranch | 1 hrs
| Retail_tblInstalmentHdr_MaxiCash_Singapore | 1 hrs
| Retail_tblInstalmentItem_MaxiCash_Singapore | 1 hrs
| Retail_tblInsCustOrder_MaxiCash_Singapore | 1 hrs
| Retail_tblDepOffset_Common | 2 hrs
| Retail_tblTransDet_Common | 2 hrs
| Retail_tblStk_Jewellery_Singapore | 1 hrs
| Retail_tblStk_Common | 2 hrs
| Retail_tblCustOrder_Common | 2 hrs
| Retail_tblStk_MaxiCash_Singapore | 1 hrs
| Retail_tblStkBag_MaxiCash_Singapore | 1 hrs
| Retail_tblstkWatch_MaxiCash_Singapore | 1 hrs
| Retail_tblPromorep_Common | 2 hrs
| Retail_tblTransHdr_Common | 2 hrs
| Retail_tblMPromoRep_Common | 2 hrs
| Retail_tblTransDet_MaxiCash_Singapore | 1 hrs
| Retail_tblCustServDet_Common | 2 hrs
| Retail_tblCustomer_Jewellery_Singapore | 1 hrs
| Retail_tblCustomer_MaxiCash_Singapore | 1 hrs
| Retail_tblCustomer_Common | 2 hrs
| Retail_tblCust_Membership_Common | 2 hrs
| Retail_tblSecUser_Common | 2 hrs
| Retail_tblIndvStoreAnalysTar_Common | 1 hrs
| Retail_tblIndvStoreAnalysTar_Jewellery_Singapore | 1 hrs
| Retail_tblSecUser_Common | 2 hrs
Report3 | Inventory_Inv_tblBulk_Common | 2 hrs
| Inventory_Inv_tblMaster_Common master_Blk_TradeInPurpose | 2 hrs
| Inventory_Inv_tblPurpose_Common | 2 hrs
| Retail_tblMonthEndBalance_Common | 2 hrs
| Retail_tblSecGroups_Common | 2 hrs
| Validating and scheduling the pipeline | 20 hrs
| Total | 127 hrs

## Effort Estimation for Datamart
Effort Estimation to setup Datawarehouse_corp in synapse
Report Name | Tables Need in Datamart | Effort needed to create pipeline
| Schema creation in datamart. | 4 hrs
Report 1 | Master_Branch | 3 hrs
| v_Today_Retail_Transaction | 6 hrs
Report 2 | Lookup_Items_CategoryLevel1 | 4 hrs
| Lookup_Customer_Information | 3 hrs
| Lookup_Pawner_Information | 4 hrs
| Lookup_Pawner_Personal_Info | 3 hrs
| Lookup_Product_Line | 3 hrs
| Lookup_Staff | 3 hrs
| Lookup_Store_Target | 3 hrs
| Txn_Sales | 5 hrs
| Lookup_PLMS_Others | 2 hrs
| Lookup_Items | 6 hrs
Report 3 | Lookup_bulkin | 3 hrs
| Summary_Item_Holder_and_Movement | 3 hrs
| Total | 55 hrs

## Effort estimation for changes in Tableau
Report Name | Activity needed | Time taken
Report 1 | Downloading and analysing existing model | 6 hrs
| Creating Data model using Synapse server | 1 hrs
| Solving column issues in dashboard | 1 hrs
| Extraction and validation | 2 hrs
Report 2 | Downloading and analysing existing model | 6 hrs
| Creating 2 data models using synapse server | 6 hrs
| Solving column issues in dashboards | 3 hrs
| Extraction and validation | 16 hrs
Report 3 | Downloading and analysing existing model | 6 hrs
| Creating 2 data models using synapse server | 4 hrs
| Solving column issues in dashboards | 2 hrs
| Extraction and validation | 8 hrs
| Publishing reports to server and scheduling | 2 hrs
| Total | 63 hrs